## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I want to study RAG architecture, multi-agent query resolution patterns, embeddings, chunking and vector search so that I can choose suitable technologies. | MUST HAVE |  | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a developer, I want to study the Web Speech API (speech-to-text and text-to-speech) so that voice interaction can be integrated later. | SHOULD HAVE |  | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US03 | As a developer, I want a system architecture, tech stack, agent roles, orchestration flow and data schemas so that the platform is designed before coding. | MUST HAVE | US01 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US04 | As a user, I want to upload PDF, DOCX, TXT and CSV documents so that I can build my own knowledge base. | MUST HAVE | US03 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US05 | As a user, I want document text extracted, cleaned and normalised so that content is ready for chunking. | MUST HAVE | US04 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US06 | As a system, I want documents split into chunks with suitable size and overlap so that retrieval is precise. | MUST HAVE | US05 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US07 | As a system, I want embeddings generated and indexed in ChromaDB with document and chunk metadata so that semantic search is possible. | MUST HAVE | US06 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US08 | As a tester, I want ingestion validated for all supported file formats so that uploads are reliable. | MUST HAVE | US07 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US09 | As a user, I want semantic retrieval of the most relevant chunks for my question so that I find the right information. | MUST HAVE | US07 | Vidyashree Metri | 3- Completed
Sprint 1 | Sprint 1 | US10 | As a tester, I want retrieval validated on two domains using factual, procedural, comparative and unavailable-information queries (Top-1, Top-3, Top-5) so that quality is known. | MUST HAVE | US09 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US11 | As a user, I want my query classified as factual, procedural, comparative or ambiguous with a structured output so that it follows the right path. | MUST HAVE | US10 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US12 | As a user, I want queries routed to the right resolution flow and ambiguous ones marked for clarification so that answers are reliable. | MUST HAVE | US11 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US13 | As a user, I want a Retrieval Agent that ranks Top-K chunks by relevance and preserves metadata so that evidence is traceable. | MUST HAVE | US09 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US14 | As a user, I want low-confidence chunks filtered and no-result cases handled so that weak evidence is not used. | MUST HAVE | US13 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US15 | As a user, I want grounded answers generated only from retrieved context so that hallucinated information is avoided. | MUST HAVE | US13, US14 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US16 | As a user, I want source attribution and a confidence indicator with every answer so that I can judge reliability. | MUST HAVE | US15 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US17 | As a system, I want an orchestration layer with a standard agent request/response format so that agents work in sequence automatically. | MUST HAVE | US11, US13, US15 | Vidyashree Metri | 3- Completed
Sprint 2 | Sprint 2 | US18 | As a system, I want error handling for classification, retrieval, empty-result and generation failures so that the pipeline never stops silently. | MUST HAVE | US17 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US19 | As a user, I want ambiguous, incomplete and multi-part queries detected and targeted follow-up questions asked so that I get accurate answers. | MUST HAVE | US12 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US20 | As a user, I want my original query and clarification combined into a refined query so that it is resolved correctly. | MUST HAVE | US19 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US21 | As a user, I want conversation memory that keeps only relevant context so that follow-up questions work without repeating myself. | MUST HAVE | US17 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US22 | As a user, I want to speak my query using the Web Speech API, see the transcript and get error handling so that I can interact by voice. | SHOULD HAVE | US17, US02 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US23 | As a user, I want responses read aloud with start, pause, resume, stop and voice settings so that I can listen to answers. | SHOULD HAVE | US22 | Vidyashree Metri | 3- Completed
Sprint 3 | Sprint 3 | US24 | As a user, I want a Response Transparency Panel with sources, chunks, scores, metadata, citations and confidence so that I can verify every answer. | MUST HAVE | US16 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US25 | As an administrator, I want every query recorded with type, resolution status, documents, confidence and clarification need so that usage can be analysed. | MUST HAVE | US17 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US26 | As an administrator, I want repeated unanswered queries and common themes identified as knowledge gaps so that I know which documents to add. | MUST HAVE | US25 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US27 | As an administrator, I want an analytics dashboard and API endpoints with filters so that I can monitor performance. | MUST HAVE | US25, US26 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US28 | As a tester, I want end-to-end testing across three knowledge domains (AI, Agriculture/IoT, NLP) so that the whole platform is validated. | MUST HAVE | US01 to US27 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US29 | As a developer, I want retrieval, prompts, routing, memory and voice handling optimised so that answer quality and reliability improve. | SHOULD HAVE | US28 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US30 | As a student, I want technical documentation of architecture, agents, pipelines, data models and APIs so that the system is fully documented. | MUST HAVE | US28 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US31 | As a student, I want a final project report covering design, implementation, testing, results, limitations and future work so that it can be submitted. | MUST HAVE | US28, US30 | Vidyashree Metri | 3- Completed
Sprint 4 | Sprint 4 | US32 | As a student, I want a final demonstration across multiple knowledge domains, including analytics and knowledge gaps, so that all features are shown. | MUST HAVE | US28, US31 | Vidyashree Metri | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 90 | 81.3 | 78.7 | 69.3 | 66.7 | 60 | 50 | 43.3 | 40.7 | 35 | 28 | 17.3 | 14.7 | 8 | 0
SPRINT 1 BACKLOG
US01 | T1.1 | Study RAG architecture and end-to-end retrieval pipelines | 2026-08-15 | 2026-08-15 | Vidyashree Metri | Design | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | T1.2 | Study multi-agent patterns, embeddings, chunking strategies and vector search | 2026-08-15 | 2026-08-17 | Vidyashree Metri | Design | 3- Completed | 8 | 5.3 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US02 | T1.3 | Study Web Speech API for speech-to-text and text-to-speech | 2026-08-17 | 2026-08-17 | Vidyashree Metri | Design | 3- Completed | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T1.4 | Create system architecture diagram and select the tech stack | 2026-08-17 | 2026-08-19 | Vidyashree Metri | Design | 3- Completed | 8 | 8 | 8 | 5.3 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T1.5 | Define agent responsibilities, orchestration flow and data schemas | 2026-08-19 | 2026-08-20 | Vidyashree Metri | Design | 3- Completed | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T1.6 | Set up GitHub repository and submit architecture and tech stack (28 Aug) | 2026-08-20 | 2026-08-20 | Vidyashree Metri | Others | 3- Completed | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T1.7 | Build document upload module for PDF, DOCX, TXT and CSV | 2026-08-20 | 2026-08-21 | Vidyashree Metri | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T1.8 | Implement text extraction and cleaning/normalisation | 2026-08-21 | 2026-08-23 | Vidyashree Metri | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.3 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T1.9 | Implement chunking strategy (chunk size and overlap) | 2026-08-23 | 2026-08-24 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
US07 | T1.10 | Generate embeddings and index chunks in ChromaDB with metadata | 2026-08-24 | 2026-08-25 | Vidyashree Metri | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0
US08 | T1.11 | Validate ingestion across all supported file formats | 2026-08-25 | 2026-08-25 | Vidyashree Metri | Unit Test | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0
US09 | T1.12 | Build semantic search RAG retrieval pipeline | 2026-08-25 | 2026-08-27 | Vidyashree Metri | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.3 | 2.7 | 0 | 0
US10 | T1.13 | Create test queries and evaluate Top-1, Top-3, Top-5 retrieval on two domains | 2026-08-27 | 2026-08-28 | Vidyashree Metri | Unit Test | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
US10 | T1.14 | Document retrieval performance, limitations and improvements for Milestone 2 | 2026-08-28 | 2026-08-28 | Vidyashree Metri | Others | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 3 | Different PDF/DOCX layouts produced noisy extracted text. | Added a cleaning and normalisation step before chunking.
Sprint 1 | 8 | Choosing a chunk size and overlap that keep context but still retrieve precisely. | Tested chunk settings with sample queries and checked Top-K results.
Sprint 1 | 12 | Needed sample documents from two domains to validate retrieval. | Prepared separate documents for each domain and created test queries.
Sprint 2 | 4 | Classifier confused ambiguous queries with factual queries. | Tuned classification prompts and marked ambiguous queries for clarification.
Sprint 2 | 9 | Local Llama 3.2 responses were slow and resource heavy. | Limited the prompt context to the top-K retrieved chunks.
Sprint 3 | 5 | Web Speech API behaved differently across browsers and microphone permission errors occurred. | Added error handling and an unsupported-browser message.
Sprint 3 | 10 | Follow-up questions such as "Why is it important?" lost their context. | Passed the relevant previous query and answer through the Conversation Memory Agent.
Sprint 4 | 4 | Repeated test queries inflated the unanswered count in analytics. | Interpreted the overall answer rate together with the clean validation tests.
Sprint 4 | 9 | Query box kept the previous text, so follow-up queries were combined with it. | Workaround: clear the query box before a follow-up; fix planned.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-08-15 | 2026-08-28 | Vidyashree Metri | Write small test queries after each ingestion step. | Test with only a single document. | Document the architecture and data flow. | Used sample documents from two domains for validation and submitted the architecture and tech stack on 28 Aug.
2 | 2 | 2026-08-29 | 2026-09-11 | Vidyashree Metri | Log retrieval distances for every query. | Pass weakly related chunks to the LLM. | Use structured outputs between agents. | Applied a relevance threshold (1.5) and insufficient-information handling.
3 | 3 | 2026-09-12 | 2026-09-25 | Vidyashree Metri | Test voice features on different browsers. | Rely only on typed queries for validation. | Show sources and scores with every answer. | Added error handling for microphone permissions and unsupported browsers.
4 | 4 | 2026-09-26 | 2026-10-09 | Vidyashree Metri | Separate clean validation queries from repeated test queries in analytics. | Count clarification requests as unanswered queries. | Run end-to-end tests across all three domains. | Logged defects in the Defect Tracker and documented limitations in the final report.
5
6
7

## Sprint 2 Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 86 | 76.7 | 73.3 | 67 | 60.7 | 57.3 | 51 | 45 | 37 | 29 | 22.7 | 19.3 | 13 | 8 | 0
SPRINT 2 BACKLOG
US11 | T2.1 | Define classification rules and prompts for the four query types | 2026-08-29 | 2026-08-29 | Vidyashree Metri | Design | 3- Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T2.2 | Implement Query Understanding Agent with structured output | 2026-08-29 | 2026-08-31 | Vidyashree Metri | Coding | 3- Completed | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T2.3 | Implement query routing and ambiguity marking | 2026-08-31 | 2026-09-01 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T2.4 | Implement Retrieval Agent (Top-K, ranking, metadata) | 2026-09-01 | 2026-09-03 | Vidyashree Metri | Coding | 3- Completed | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | T2.5 | Implement configurable low-confidence filtering and no-result handling | 2026-09-03 | 2026-09-04 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T2.6 | Design grounded-answer prompts for Llama 3.2 (Ollama) | 2026-09-04 | 2026-09-05 | Vidyashree Metri | Design | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T2.7 | Implement Response Generation Agent | 2026-09-05 | 2026-09-06 | Vidyashree Metri | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US16 | T2.8 | Add source attribution and confidence indicator | 2026-09-06 | 2026-09-07 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
US17 | T2.9 | Build orchestration layer and standard agent request/response format | 2026-09-07 | 2026-09-09 | Vidyashree Metri | Coding | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0
US18 | T2.10 | Implement error handling for classification, retrieval, empty results and generation | 2026-09-09 | 2026-09-10 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0
US11 | T2.11 | Test classification accuracy with queries from two domains | 2026-09-10 | 2026-09-11 | Vidyashree Metri | Unit Test | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0
US17 | T2.12 | End-to-end test of query resolution across both domains | 2026-09-11 | 2026-09-11 | Vidyashree Metri | Integration Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Sprint 3 Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 82 | 77 | 69 | 63 | 56.7 | 53.3 | 47 | 40 | 34 | 29 | 22 | 18 | 12 | 5 | 0
SPRINT 3 BACKLOG
US19 | T3.1 | Implement ambiguity detection (unclear terms, missing context, multi-part queries) | 2026-09-12 | 2026-09-13 | Vidyashree Metri | Coding | 3- Completed | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US19 | T3.2 | Generate targeted clarification questions | 2026-09-13 | 2026-09-14 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US20 | T3.3 | Combine original query and clarification into a refined query and re-route | 2026-09-14 | 2026-09-15 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US21 | T3.4 | Build Conversation Memory Agent (store and select relevant context) | 2026-09-15 | 2026-09-17 | Vidyashree Metri | Coding | 3- Completed | 10 | 10 | 10 | 10 | 6.7 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US21 | T3.5 | Limit history passed to the LLM and handle missing context | 2026-09-17 | 2026-09-18 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US22 | T3.6 | Integrate Web Speech API voice input with transcript display and controls | 2026-09-18 | 2026-09-19 | Vidyashree Metri | Coding | 3- Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US22 | T3.7 | Handle recognition errors, microphone permissions and unsupported browsers | 2026-09-19 | 2026-09-20 | Vidyashree Metri | Coding | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US23 | T3.8 | Implement text-to-speech with start, pause, resume, stop and voice selection | 2026-09-20 | 2026-09-21 | Vidyashree Metri | Coding | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0
US24 | T3.9 | Build Response Transparency Panel (sources, chunks, scores, citations, expandable view) | 2026-09-21 | 2026-09-23 | Vidyashree Metri | Coding | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0
US24 | T3.10 | Show low-confidence and insufficient-information messages | 2026-09-23 | 2026-09-24 | Vidyashree Metri | Coding | 3- Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0
US19 | T3.11 | Test clarification, memory, voice and transparency across domains | 2026-09-24 | 2026-09-25 | Vidyashree Metri | System Test | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Sprint 4 Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 100 | 88 | 80 | 76 | 61 | 52 | 43 | 35 | 26 | 12.7 | 5.3 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US25 | T4.1 | Implement query analytics recording (type, status, confidence, documents, response time) | 2026-09-26 | 2026-09-26 | Vidyashree Metri | Coding | 3- Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US26 | T4.2 | Implement knowledge gap detection and common-query analysis | 2026-09-26 | 2026-09-27 | Vidyashree Metri | Coding | 3- Completed | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US27 | T4.3 | Build analytics dashboard and API endpoints with filters | 2026-09-27 | 2026-09-29 | Vidyashree Metri | Coding | 3- Completed | 12 | 12 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US28 | T4.4 | Prepare document collections for AI, Agriculture/IoT and NLP domains | 2026-09-29 | 2026-09-29 | Vidyashree Metri | Others | 3- Completed | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US28 | T4.5 | Run end-to-end tests: factual, procedural, comparative and ambiguous queries | 2026-09-29 | 2026-09-30 | Vidyashree Metri | System Test | 3- Completed | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0
US28 | T4.6 | Test multi-turn memory, context switching, voice and transparency | 2026-09-30 | 2026-10-01 | Vidyashree Metri | System Test | 3- Completed | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
US29 | T4.7 | Tune retrieval threshold, prompts, routing, memory and voice handling | 2026-10-01 | 2026-10-02 | Vidyashree Metri | Others | 3- Completed | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0
US28 | T4.8 | Retest after corrections and log defects | 2026-10-02 | 2026-10-03 | Vidyashree Metri | Regression Test | 3- Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0
US30 | T4.9 | Write technical documentation (architecture, agents, pipelines, data models, APIs) | 2026-10-03 | 2026-10-04 | Vidyashree Metri | Others | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0 | 0
US31 | T4.10 | Prepare final project report | 2026-10-04 | 2026-10-05 | Vidyashree Metri | Others | 3- Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 0
US32 | T4.11 | Prepare final demonstration with multiple knowledge domains | 2026-10-04 | 2026-10-09 | Vidyashree Metri | Others | 2- In Progress | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6.7 | 5.3
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work