## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vidyashree Metri | 2026-10-04 | Follow-up query returns a garbled answer ("Why is Why is it important?…") and "Information not found" when the query box still holds the earlier question. | Sprint 4 | Vidyashree Metri | Logical | Workaround: clear the query box before typing a follow-up. Planned: reset the input after each run. |  | Open | M3.2. Seen at 7:08 PM during multi-turn testing.
2 | Vidyashree Metri | 2026-10-04 | Clarification requests (e.g. "Tell me about sensors.") are logged as Unanswered with confidence 0.00, which lowers the answer rate. | Sprint 4 | Vidyashree Metri | Logical | Planned: log clarification requests as a separate status. |  | Open | M4.1. Visible in the Query Analytics log.
3 | Vidyashree Metri | 2026-10-04 | Refined query after clarification repeats the original text (e.g. "tell me about sensors. tell me about sensors.") in analytics. | Sprint 4 | Vidyashree Metri | Logical | Planned: de-duplicate when combining the original query and clarification. |  | Open | M3.1 / M4.1. Appears as a repeated common query.
4 | Vidyashree Metri | 2026-10-04 | Two identical "Low confidence" banners are displayed for a single answer. | Sprint 4 | Vidyashree Metri | User Interface | Planned: show one confidence banner per answer. |  | Open | M2.3 / M3.4. Seen on answered queries.
5 | Vidyashree Metri | 2026-10-04 | "Please enter a question." message is shown in the answer area while the microphone is listening or converting speech. | Sprint 4 | Vidyashree Metri | User Interface | Planned: hide the empty-query message while voice input is active. |  | Open | M3.3. Seen at 6:43 PM and 7:03 PM.
6 | Vidyashree Metri | 2026-10-04 | Misspelled or misrecognised queries (e.g. "What is a soil mitre sensor?") are counted as separate knowledge gaps. | Sprint 4 | Vidyashree Metri | Logical | Planned: add spelling tolerance or query normalisation. |  | Open | M4.1. Visible in the Knowledge Gap Detection list.
7 | Vidyashree Metri | 2026-10-04 | Knowledge domain counts (40 + 21 + 6 + 71 = 138) do not add up to the total recorded queries (132). | Sprint 4 | Vidyashree Metri | Logical | Planned: verify how multi-domain queries are counted. |  | Open | M4.1. Analytics 02 vs total queries.
8 | Vidyashree Metri | 2026-10-04 | Analytics reports 0 low-confidence responses although answers show "Low confidence" banners (retrieval confidence 0.38 to 0.45). | Sprint 4 | Vidyashree Metri | Logical | Planned: use retrieval confidence for the low-confidence count, or explain the difference in the report. |  | Open | M4.1. Dashboard vs answer panel.
9 | Vidyashree Metri | 2026-10-04 | Browser console reports favicon.ico failing to load (404 File not found). | Sprint 4 | Vidyashree Metri | Others | Planned: add a favicon file to the project folder. |  | Open | Seen in the browser DevTools console.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others